## Project Settings
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 32.6 | 25.4 | 36.4
Planned Time | 0.18542 |  | 1899-12-31 08:00
Actual Tiempo |  | 0.20139 | 1899-12-31 04:26
CPI (Cost-Performance Index) |  |  | 1.13
% Reuse | 13.8% | 9.84% | 8.21%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 4.39 | 0 | 3.87
Total Defects/KLOC or equivalent | 15.4 | 40.7 | 18.4
Yield % | 100% | 100% | 100%
Code Review Rate | 570 | 284 | 580
% Appraisal COQ | 12.8% | 19.7% | 14%
% Failure COQ | 7.77% | 8.97% | 7.97%
COQ A/F Ratio | 1.65 | 2.19 | 1.75
PQI | 0.09 | 0.89 | 0.14
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:01 AM el 5/04/2017

## Overall Metrics
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 32.6 | 25.4 | 36.4
Planned Time | 0.18542 |  | 1899-12-31 08:00
Actual Tiempo |  | 0.20139 | 1899-12-31 04:26
CPI (Cost-Performance Index) |  |  | 1.13
% Reuse | 13.8% | 9.84% | 8.21%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 4.39 | 0 | 3.87
Total Defects/KLOC or equivalent | 15.4 | 40.7 | 18.4
Yield % | 100% | 100% | 100%
Code Review Rate | 570 | 284 | 580
% Appraisal COQ | 12.8% | 19.7% | 14%
% Failure COQ | 7.77% | 8.97% | 7.97%
COQ A/F Ratio | 1.65 | 2.19 | 1.75
PQI | 0.09 | 0.89 | 0.14
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:02 AM el 5/04/2017

## Program Size
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 165 | 235 | 552
Deleted (D) | 3 | 0 | 66
Modified (M) | 25 | 10 | 47
Added (A) | 120 | 113 | 987
Reused (R) | 45 | 38 | 112
Added and Modified (A+M) | 145 | 123 | 1034
Total Size (T) | 327 | 386 | 1365
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 172 | 123 | 846
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:02 AM el 5/04/2017

## Time In Phase
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.043056 | 0.039583 | 0.26875 | 22.7%
DiseÃ±o | 0.018056 | 0.047222 | 0.14444 | 12.2%
RevisiÃ³n de DiseÃ±o | 0.013194 | 0.021528 | 0.090972 | 7.68%
CodificaciÃ³n | 0.066667 | 0.036806 | 0.38819 | 32.8%
RevisiÃ³n de CodificaciÃ³n | 0.010417 | 0.018056 | 0.074306 | 6.27%
CompilaciÃ³n | 0.0055556 | 0.00069444 | 0.030556 | 2.58%
Pruebas | 0.0090278 | 0.017361 | 0.063889 | 5.39%
Postmortem | 0.019444 | 0.020139 | 0.12361 | 10.4%
Total | 0.18542 | 0.20139 | 1899-12-31 04:26
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:03 AM el 5/04/2017

## Defects Injected
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.32 | 0 | 2 | 10.5%
DiseÃ±o | 0.96 | 3 | 9 | 47.4%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.32 | 2 | 4 | 21.1%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.64 | 0 | 4 | 21.1%
Total | 2.23 | 5 | 19
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:03 AM el 5/04/2017

## Defects Removed
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.32 | 0 | 2 | 10.5%
DiseÃ±o | 0.16 | 1 | 2 | 10.5%
RevisiÃ³n de DiseÃ±o | 0.32 | 2 | 4 | 21.1%
CodificaciÃ³n | 0.48 | 0 | 3 | 15.8%
RevisiÃ³n de CodificaciÃ³n | 0.32 | 2 | 4 | 21.1%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.64 | 0 | 4 | 21.1%
Total | 2.23 | 5 | 19
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:04 AM el 5/04/2017

## Defect Removal Efficiency
/Proyecto/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.01 | 3.87 | 1.83
Defects/Hour - Code Review | 1.25 | 4.62 | 2.24
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 3.02 | 0 | 2.61
DRL (DLDR/UT) | 0.34 | 1.48 | 0.7
DRL (Code Review/UT) | 0.41 | 1.77 | 0.86
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:05 AM el 5/04/2017